## Sheet1
Sprint | Sprint Goal | Milestone | Milestone Description | Planned completion date
Sprint-1 Planning | Capacity planning, story Pointing, Prioritization
Sprint-1 | Catalogue Functionality | Milestone-1 | Initial UI mockups | 2018-04-09
Sprint-1 Review | Walkthrough functionality/code to leads
Sprint-1 Retrospection | Understand 4 L's(liked, learned, lacked and longed for)
Sprint-2 Planning | Capacity Planning, Story Pointing, Prioritization
Sprint-2 | Feedback Categorization | Milestone-1 | Data population for database | 2018-04-15
|  | Milestone-2 | Modelling feedback into topics | 2018-04-24
Sprint-2 Review | Walkthrough functionality/code to leads
Sprint-2 Retrospection | Understand 4 L's(liked, learned, lacked and longed for)
Sprint-3 Planning | Capacity Planning, Story Pointing, Prioritization
Sprint-3 | Feedback summarization and UI | Milestone-1 | Implement topic summarization | 2018-05-02
|  | Milestone-2 | UI for the home page | 2018-05-07
Sprint-3 Review | Walkthrough functionality/code to leads
Sprint-3 Retrospection | Understand 4 L's(liked, learned, lacked and longed for)
Sprint-4 Planning | Capacity Planning, Story Pointing, Prioritization
Sprint-4 | Opinion mining and UI | Milestone-1 | Sentiment analysis of feedback | 2018-05-11
|  | Milestone-2 | UI for all the web pages | 2018-05-17
Sprint-4 Review | Walkthrough functionality/code to leads
Sprint-4 Retrospection | Understand 4 L's(liked, learned, lacked and longed for)
Sprint-5 Planning | Capacity Planning, Story Pointing, Prioritization
Sprint-5 | Product notification functionality | Milestone-1 | user friends data gathering which includes chase and non chase customers | 2018-05-23
|  | Milestone-2 | Implement notification sending functionality | 2018-05-28
Sprint-5 Review | Walkthrough functionality/code to leads
Sprint-5 Retrospection | Understand 4 L's(liked, learned, lacked and longed for)